## DWG
DRAWINGS
Type | Deliverable | Reference (Must be Unique across all tabs) | Planned release date | System (MEP)
DWG | DWG PADDINGTON 10 | PAD-2255-XC-SZ-DD-LN-02001 | 2021-07-13
DWG | DWG PADDINGTON 11 | PAD-2255-XC-SZ-DD-LN-02002 | 2021-08-13
DWG | DWG Stone Kerb | PAD-8100-ZZ-ZZ-DR-LN-00013 | 2022-08-13

## TS
TECHNICAL SUBMISSIONS
Type | Deliverable | Reference (Must be Unique across all tabs) | Planned release date | Actual release date
TS | Ad-1 Access Pits | 527300-TS-003 | 2020-12-11
TS | Ad-2 Access Pits | 527300-TS-023 | 2020-12-10
TS | Ad-3 Access Pits | 527300-TS-004 | 2020-12-09
TS | Ad-4 Access Pits | 527300-TS-005 | 2020-12-05

## SCH
Schematics
Type | Deliverable | Reference (Must be Unique across all tabs) | Planned release date
SCH | MJLJJ 1 | PAD-8880-SS-SS-D-01 | 2022-01-21
SCH | MJLJJ 1 | PAD-8880-SS-SS-D-02 | 2022-01-02
SCH | MJLJJ 1 | PAD-8880-SS-SS-D-03 | 2022-01-01
SCH | MJLJJ 1 | PAD-8880-SS-SS-D-04 | 2022-01-21

## MDL
Model release
Type | Deliverable | Reference (Must be Unique across all tabs) | Planned release date
MDL | EXT DUBLICATE | 0-ss-SS-M3-001 | 2021-11-02
MDL | EXT DUBLICATE | 0-ss-SS-M3-001 | 2021-11-03
MDL | EXT Stone NULL REFERENCE |  | 2021-11-04
FORMULAS ONLY WORK TILL ROW 300

## CPD
CPD Inputs
Type | Deliverable | Reference (Must be Unique across all tabs) | Planned release date
CPD | CPD Inputs | CPD -00 | 2021-11-03
CPD | CPD Inputs | CPD -01 | 2021-11-03
CPD | CPD Inputs | CPD -02 | 2021-11-03
FORMULAS ONLY WORK TILL ROW 300

## EDA
External Design Audits
Type | Deliverable | Reference (Must be Unique across all tabs) | Planned release date
EDA | EDA TEST | Asdad-99-00 | 1933-06-07 04:51
EDA | EDA TEST | Asdad-99-01 | 2022-03-02
EDA | EDA TEST | Asdad-99-02 | 2022-12-12
FORMULAS ONLY WORK TILL ROW 300

## TDRG
2D Tender Information
Type | Deliverable | Reference (Must be Unique across all tabs) | Planned release date
TDRG | TDRG Del | Del-22-22 | 2022-11-11
TDRG | TDRG Del | Del-22-23 | 2022-11-11
TDRG | TDRG Del | Del-22-24 | 2022-11-11

## TENQ
Tender Enquiries
Type | Deliverable | Reference (Must be Unique across all tabs) | Planned release date
TENQ | TENQ Del | del-22-AA-01 | 2022-10-14
TENQ | TENQ Del | del-22-AA-02 | 2022-10-14
TENQ | TENQ Del | del-22-AA-03 | 2022-10-14
FORMULAS ONLY WORK TILL ROW 300

## CFO
Commercial Full Orders
Type | Deliverable | Reference (Must be Unique across all tabs) | Planned release date
CFO | CFO |  | 2020-10-10
CFO | CFO | CFO-22-02 | 2020-10-10
CFO | CFO | CFO-22-03 | 2020-10-10
FORMULAS ONLY WORK TILL ROW 300

## DSC
Dynamic System Checks
Type | Deliverable | Reference (Must be Unique across all tabs) | Planned release date
DSC | DSC | DSC-1 | 2022-01-01
DSC | DSC | DSC-2 | 2022-01-01
DSC | DSC | DSC-3 | 2022-01-01
FORMULAS ONLY WORK TILL ROW 300

## PSD
Project specific documents
Type | Deliverable | Reference (Must be Unique across all tabs) | Planned release date
PSD | PSD del | PSD-1 | 2021-08-04
PSD | PSD del2 | PSD-2 | 2021-08-04
PSD | PSD del3 | PSD-3 | 2021-08-04
FORMULAS ONLY WORK TILL ROW 300

## RAMS
RISK ASSESSMENTS AND METHOD STATEMENTS
Type | Deliverable | Reference (MustbeUniqueacrossalltabs) | Plannedreleasedate | release
RAMS | PAMS del | Ram — 1 | 2021-06-10 | 2021-04-25
RAMS | PAMS del | Ram — 2 | 2021-06-10 | 2021-04-25
RAMS | PAMS del | Ram — 3 | 2021-06-10 | 2021-04-25
Note on E2: Nelson, David: Column Locked
FORMULAS ONLY WORK TILL ROW 300

## TWS
TEMPORARY WORK SCHEDULE / REQUIREMENTS
Type | Deliverable | Reference (Must be Unique across all tabs) | Planned release date
TWS | TWS del | Tws-01 | 2022-02-02
TWS | TWS del 2 | Tws-02 | 2022-02-02
TWS | TWS del 3 | Tws-03 | 2022-02-02
TWS | TWS del dublicate | Tws-01 | 2022-02-02
FORMULAS ONLY WORK TILL ROW 300

## CMS
COMMISSIONING METHOD STATEMENTS
Type | Deliverable | Reference (Must be Unique across all tabs) | Planned release date | System
CMS | test | MMEP-CMS-001 | 2021-06-06 | Mechanical
CMS | CMS del | del-01-22-33-FF-FFF-2221-01 | 2022-06-01
CMS | CMS del 2 | del-01-22-33-FF-FFF-2221-02 | 2022-06-01
CMS | CMS del3 empry |  | 2022-06-01
Note on E2: Nelson, David: Column Locked

## QS_QBM_P_MU
Samples, mock-ups, prototypes, benchmarks
Type | Deliverable | Reference (Must be Unique across all tabs) | Planned release date
QBM | QBM del | QBM-1 | 2021-07-26
QBM | QBM del2 | QBM-2 | 2021-07-26
QBM | QBM del3 | QBM-3 | 2021-07-26
FORMULAS ONLY WORK TILL ROW 300

## Fab_QSO
FABRICATION OR MANUFACTURE - QUALITY SIGN OFF / ITP'S within manufacturing process
Type | Deliverable | Reference (Must be Unique across all tabs) | Planned release date
Fab_QSO | Fabqso | fab-01-222-111-aaaa-1 | 2023-02-02
Fab_QSO | Fabqso2 | fab-01-222-111-aaaa-2 | 2023-02-02
Fab_QSO | Fabqso null |  | 2023-02-02

## Ins_QSO
INSTALLATION - QUALITY SIGN OFF / ITP's (e.g. pre pour inspections, torquing bolts, line & level survey, weld inspections, drainage testing, flood testing etc) - QA within package
Type | Deliverable | Reference (Must be Unique across all tabs) | Planned release date
Ins_QSO | INS del | INS-2222-0000-AA-1 | 2022-02-02
Ins_QSO | INS del | INS-2222-0000-AA-2 | 2022-02-02
Ins_QSO | INS del | INS-2222-0000-AA-3 | 2022-02-02

## QHP
INSTALLATION - QUALITY HOLD POINTS
Type | Deliverable | Reference (Must be Unique across all tabs) | Planned release date
QHP | QHP DEL | DDDD-2222-111-QHP-1 | 2022-02-02
QHP | QHP DEL2 NULL |  | 2022-02-02
QHP | QHP DEL3 | DDDD-2222-111-QHP-1 | 2022-02-02

## ATP1
INSTALLATION SIGNED OFF
Type | Deliverable | Reference (Must be Unique across all tabs) | Planned release date
ATP1 | atp1 | ATP-1111-1111-AAA-1 | 2022-02-02
ATP1 | atp1 NULL DATE HELLO KIPOD | ATP-1111-1111-AAA-2
ATP1 | atp1 | ATP-1111-1111-AAA-3 | 2022-02-02

## ATP2
PRE-COMMISSIONING COMPLETE
Type | Deliverable | Reference (Must be Unique across all tabs) | Planned release date
ATP2 | ATP2 DEL | ATP-0000-AAAA-1 | 2022-02-02
ATP2 | ATP2 DEL | ATP-0000-AAAA-2 | 2022-02-02
ATP2 | ATP2 DEL | ATP-0000-AAAA-3 | 2022-02-02
FORMULAS ONLY WORK TILL ROW 300

## ATP3
COMMISSIONING COMPLETE
Type | Deliverable | Reference (Must be Unique across all tabs) | Planned release date
ATP3 | APT3 DLE1 | ATP-8888-7777 | 2025-05-05
ATP3 | APT3 DLE1 | ATP-8888-77772 | 2025-05-05
ATP3 | APT3 DLE13 | ATP-8888-77773 | 2025-05-05
ATP3 | APT3 DLE1 | ATP-8888-77774 | 2025-05-05

## HOD
HANDOVER DOCUMENTATION - AS BUILT DRAWINGS / O&M's [inc. certification]
Type | Deliverable | Reference (Must be Unique across all tabs) | Planned release date
HOD | ITS HOD AS HELL | 222-HOD-555 | 2022-02-02
HOD | ITS HOD AS HELL2 | 222-HOD-5553 | 2022-02-02
HOD | ITS HOD AS HELL NULLREF |  | 2022-02-02
HOD | ITS HOD AS HELL NULL DATE | 222-HOD-555
FORMULAS ONLY WORK TILL ROW 300

## Sheet1
Type | Deliverable | Reference (Must be Unique across all tabs) | Planned release date | Level | Space | Actual Date (BIM 360 field) | QHP
Ins_QSO | TEST
QSO
ATP
EACH QUALITY HOLD POINT WILL BE LINKED TO A NUMBER OF QSOs & ATP ACTIVITIES